## Agenda
CMS ADVENT - PROJECT GEMINIS
CDR Agenda
Date: 30-04-2026 Version: 1,0
| 01 - june | Participants | Venue | 02 - june | Participants | Venue | 03 - june | Participants | Venue | 04 - june | Participants | Venue | 05 - june | Participants | Venue
| Monday |  |  | Tuesday |  |  | Wesnesday |  |  | Thursday |  |  | Friday
0900 - 1200 | PMR | PM Havelsan PM Armada | Asmar(T) | CDR review (2) | PM Havelsan PM Armada C-320 (EIN) | Asmar(T) | CDR review (4) | PM Havelsan PM Armada C-320 (EIN) | Asmar(T) | Available |  |  | Available
1200 - 1400 | Lunch | Asmar(T) |  | Lunch | Asmar(T) |  | Lunch | Asmar(T)
1400 - 1600 | CDR review (1) | PM Havelsan PM Armada C-320 (EIN) |  | CDR review (3) | PM Havelsan PM Armada C-320 (EIN) |  | Wrap Up | PM Havelsan PM Armada |  | Available |  |  | Available

## Items to be reviewed
N° | Activity | Chilean Navy Comments
System Engineering
1 | Combat System Configuration | Drawing concept updated
2 | Platform to System Integration Design (CMS)
Engineering Support Services
3 | Preliminary CS Design Layout | Expected for May 22nd (CDR)
4 | CMS System Design | Expected for May 22nd (CDR)
5 | CMS Integration Design
6 | CMS Platform Design
7 | Emulator or Simulator? | When do you need it?, Sagitario FCS?
Critical design Review - CDR
8 | Combat System Configuration (final)
9 | Interface Control Document (ICD) | Mecanical, cables, signals, between units.
10 | Information required for System to system Integration Design
11 | Combat system Placement Detail Design